## Testcases
Transaction | Screens | Functionalities | Aut Test ID | Flow | Status | Owner | Start Date | Planned End Date | Actual End Date
New Business | Offerings | Basic Program | AUT_TS_01 | "NB > Basic Program > Additional Insured Add > Secondary Named Insured Add > UW Company Mod > Driver Info Add > Vehicle Info Add > Coverages Modification > Prior policies Entry > Billing Type 1 > 6 months schedule > Premium match>Policy Details Review>Forms trigger and ordering validation>Billing type > PC > Secondary Named Insured Del" | InProgress | Akula Srikanth | 2021-03-31 | 2021-04-03
|  | Standard Program | AUT_TS_02 | "NB > Standard Program > Organization Mod> Affinity Goup Addition>Primary Named Insured Mod>Address Add>UW Company Mod>Coverages Del>Prior policies Mod>Prior policies Del>Schedule" | InProgress | Gautham Karanam | 2021-03-31 | 2021-04-03
|  | Premium Program | AUT_TS_03 | NB > Standard Program > Organization Mod > Additional Insured Add > Additional Insured Mod > Primary Named Insured Mod>Address Mod>Policy Info Mod> Driver Info Add > Driver Info Mod>Vehicle Info Add>Coverages Mod>Prior losses entry>Prior losses Mode>Prior losses Del> Quote > UW Issues approval > Payment > Issue | InProgress | Akash Gowda | 2021-03-31 | 2021-04-03
| Policy Info | Additional Insured Add | AUT_TS_04 | NB > Premium Program > Additional Insured Add > Additional Insured Del > Secondary Named Insured Add > UW Company Mod > Driver Info Add > Vehicle Info Add > Coverages Modification > Prior policies Entry > Billing Type 1 > 6 months schedule > Premium match | InProgress | Shweta Yaradoni | 2021-03-31 | 2021-04-03
|  | Additional Insured Del | AUT_TS_05 |  | Yet2Start
|  | Additional Insured Mod | AUT_TS_06 |  | Yet2Start
|  | Secondary Named Insured Add | AUT_TS_07 |  | Yet2Start
|  | Secondary Named Insured Del | AUT_TS_08 |  | Yet2Start
|  | Secondary Named Insured Mod | AUT_TS_09 |  | Yet2Start
|  | Organization Mod | AUT_TS_10 |  | Yet2Start
|  | Affinity Goup Addition | AUT_TS_11 |  | Yet2Start
|  | Primary Named Insured Mod | AUT_TS_12 |  | Yet2Start
|  | Address Add | AUT_TS_13 |  | Yet2Start
|  | Address Mod | AUT_TS_14 |  | Yet2Start
|  | Policy Info Mod | AUT_TS_15 |  | Yet2Start
|  | UW Company Mod | AUT_TS_16 |  | Yet2Start
| Drivers | Driver Info Add | AUT_TS_17 |  | Yet2Start
|  | Driver Info Del | AUT_TS_18 |  | Yet2Start
|  | Driver Info Mod | AUT_TS_19 |  | Yet2Start
| Vehicles | Vehicle Info Add | AUT_TS_20 |  | Yet2Start
|  | Vehicle Info Del | AUT_TS_21 |  | Yet2Start
|  | Vehicle Info Mod | AUT_TS_22 |  | Yet2Start
| Coverages | Coverages Add | AUT_TS_23 |  | Yet2Start
|  | Coverages Del | AUT_TS_24 |  | Yet2Start
|  | Coverages Mod | AUT_TS_25 |  | Yet2Start
| Risk Analysis | Prior policies entry | AUT_TS_26 |  | Yet2Start
|  | Prior policies Mod | AUT_TS_27 |  | Yet2Start
|  | Prior policies Del | AUT_TS_28 |  | Yet2Start
|  | Prior losses entry | AUT_TS_29 |  | Yet2Start
|  | Prior losses Mod | AUT_TS_30 |  | Yet2Start
|  | Prior losses Del | AUT_TS_31 |  | Yet2Start
|  | UW Issues approval | AUT_TS_32 |  | Yet2Start
| Policy Review | Policy Details Review | AUT_TS_33 |  | Yet2Start
| Forms | Forms trigger and ordering validation | AUT_TS_34 |  | Yet2Start
| Billing | Billing type | AUT_TS_35 |  | Yet2Start
|  | Schedule | AUT_TS_36 |  | Yet2Start
|  | Premium | AUT_TS_37 |  | Yet2Start
Change | Offerings | Basic Program | AUT_TS_38 |  | Yet2Start
| Policy Info | Additional Insured Add | AUT_TS_39 |  | Yet2Start
|  | Additional Insured Del | AUT_TS_40 |  | Yet2Start
|  | Additional Insured Mod | AUT_TS_41 |  | Yet2Start
|  | Secondary Named Insured Add | AUT_TS_42 |  | Yet2Start
|  | Secondary Named Insured Del | AUT_TS_43 |  | Yet2Start
|  | Secondary Named Insured Mod | AUT_TS_44 |  | Yet2Start
|  | Organization Mod | AUT_TS_45 |  | Yet2Start
|  | Affinity Goup Addition | AUT_TS_46 |  | Yet2Start
|  | Primary Named Insured Mod | AUT_TS_47 |  | Yet2Start
|  | Address Add | AUT_TS_48 |  | Yet2Start
|  | Address Mod | AUT_TS_49 |  | Yet2Start
|  | Policy Info Mod | AUT_TS_50 |  | Yet2Start
|  | UW Company Mod | AUT_TS_51 |  | Yet2Start
| Drivers | Driver Info Add | AUT_TS_52 |  | Yet2Start
|  | Driver Info Del | AUT_TS_53 |  | Yet2Start
|  | Driver Info Mod | AUT_TS_54 |  | Yet2Start
| Vehicles | Vehicle Info Add | AUT_TS_55 |  | Yet2Start
|  | Vehicle Info Del | AUT_TS_56 |  | Yet2Start
|  | Vehicle Info Mod | AUT_TS_57 |  | Yet2Start
| Coverages | Coverages Add | AUT_TS_58 |  | Yet2Start
|  | Coverages Del | AUT_TS_59 |  | Yet2Start
|  | Coverages Mod | AUT_TS_60 |  | Yet2Start
| Risk Analysis | Prior policies entry | AUT_TS_61 |  | Yet2Start
|  | Prior policies Mod | AUT_TS_62 |  | Yet2Start
|  | Prior policies Del | AUT_TS_63 |  | Yet2Start
|  | Prior losses entry | AUT_TS_64 |  | Yet2Start
|  | Prior losses Mod | AUT_TS_65 |  | Yet2Start
|  | Prior losses Del | AUT_TS_66 |  | Yet2Start
|  | UW Issues approval | AUT_TS_67 |  | Yet2Start
| Policy Review | Policy Details Review | AUT_TS_68 |  | Yet2Start
| Forms | Forms trigger and ordering validation | AUT_TS_69 |  | Yet2Start
| Billing | Billing type | AUT_TS_70 |  | Yet2Start
|  | Schedule | AUT_TS_71 |  | Yet2Start
|  | Premium | AUT_TS_72 |  | Yet2Start
Cancellation | Cancellation Confirmation screen | Mid Term Cancellation | AUT_TS_73 |  | Yet2Start
|  | New Business Cancellation | AUT_TS_74 |  | Yet2Start
|  | Insured Cancellation | AUT_TS_75 |  | Yet2Start
|  | Insurer Cancellation | AUT_TS_76 |  | Yet2Start
Reinstate | Start Reinstatement | Reinstatement Reason | AUT_TS_77 |  | Yet2Start
| Risk Analysis | Prior policies entry | AUT_TS_78 |  | Yet2Start
|  | Prior policies Mod | AUT_TS_79 |  | Yet2Start
|  | Prior policies Del | AUT_TS_80 |  | Yet2Start
|  | Prior losses entry | AUT_TS_81 |  | Yet2Start
|  | Prior losses Mod | AUT_TS_82 |  | Yet2Start
|  | Prior losses Del | AUT_TS_83 |  | Yet2Start
|  | UW Issues approval | AUT_TS_84 |  | Yet2Start
Rewrite | Offerings | Change Program | AUT_TS_85 |  | Yet2Start
| Policy Info | Additional Insured Add | AUT_TS_86 |  | Yet2Start
|  | Additional Insured Del | AUT_TS_87 |  | Yet2Start
|  | Additional Insured Mod | AUT_TS_88 |  | Yet2Start
|  | Secondary Named Insured Add | AUT_TS_89 |  | Yet2Start
|  | Secondary Named Insured Del | AUT_TS_90 |  | Yet2Start
|  | Secondary Named Insured Mod | AUT_TS_91 |  | Yet2Start
|  | Organization Mod | AUT_TS_92 |  | Yet2Start
|  | Affinity Goup Addition | AUT_TS_93 |  | Yet2Start
|  | Primary Named Insured Mod | AUT_TS_94 |  | Yet2Start
|  | Address Add | AUT_TS_95 |  | Yet2Start
|  | Address Mod | AUT_TS_96 |  | Yet2Start
|  | Policy Info Mod | AUT_TS_97 |  | Yet2Start
|  | UW Company Mod | AUT_TS_98 |  | Yet2Start
| Drivers | Driver Info Add | AUT_TS_99 |  | Yet2Start
|  | Driver Info Del | AUT_TS_100 |  | Yet2Start
|  | Driver Info Mod | AUT_TS_101 |  | Yet2Start
| Vehicles | Vehicle Info Add | AUT_TS_102 |  | Yet2Start
|  | Vehicle Info Del | AUT_TS_103 |  | Yet2Start
|  | Vehicle Info Mod | AUT_TS_104 |  | Yet2Start
| Coverages | Coverages Add | AUT_TS_105 |  | Yet2Start
|  | Coverages Del | AUT_TS_106 |  | Yet2Start
|  | Coverages Mod | AUT_TS_107 |  | Yet2Start
| Risk Analysis | Prior policies entry | AUT_TS_108 |  | Yet2Start
|  | Prior policies Mod | AUT_TS_109 |  | Yet2Start
|  | Prior policies Del | AUT_TS_110 |  | Yet2Start
|  | Prior losses entry | AUT_TS_111 |  | Yet2Start
|  | Prior losses Mod | AUT_TS_112 |  | Yet2Start
|  | Prior losses Del | AUT_TS_113 |  | Yet2Start
|  | UW Issues approval | AUT_TS_114 |  | Yet2Start
| Policy Review | Policy Details Review | AUT_TS_115 |  | Yet2Start
| Forms | Forms trigger and ordering validation | AUT_TS_116 |  | Yet2Start
| Billing | Billing type | AUT_TS_117 |  | Yet2Start
|  | Schedule | AUT_TS_118 |  | Yet2Start

## Login
PrimaryKey | TD_UserName | TD_Password
SuperUser | su | gw
User1 | susa | pad
User2 | stuart | art
User3 | midas | lat
User4 | enrich | net
User5 | alex | lin
User6 | mabo | dhu
User7 | tallen | gw

## Account
PrimaryKey | TD_AccountName | TD_AccountType | TD_BillingPlan | TD_DelinquencyPlan | TD_SendInvoicesBy | TD_CompanyName
BillPlan1 | Automation10 | Insured | QA1BILLINGPLAN01 | Equity-Based Delinquency Plan | Email | Wright Construction
BillPlan2
BillPlan3
BillPlan4
BillPlan5

## Policy
PrimaryKey | TD_BillingMethod | TD_PaymentPlan | TD_CompanyName | TD_ChargesType | TD_ChargesAmount
PaymentPlan1 | Direct Bill | B Monthly 10% Down, Max 11 installments | Wright Construction | Premium | 1000
PaymentPlan2
PaymentPlan3
PaymentPlan4
PaymentPlan5

## AcctSummary
PrimaryKey | TD_AccountName | TD_PayoffAmount | TD_PolicyNumber | TD_TotalValue
AcctSumry1 |  | $1,000.00 |  | $1,000.00
AcctSumry2
AcctSumry3
AcctSumry4
AcctSumry5

## Invoice
PrimaryKey | TD_InoiveEMI
InvoiceValues1 | 11
InvoiceValues2